## WBSData
WBS | Name | Duration | Baseline Duration | % Complete | Baseline Start | Start | Baseline Finish | Finish
1 | Nutrinfo | 99d | 0d | 12% |  | 2017-07-17 08:00 |  | 2017-11-30 17:00
1.1 | Iniciação | 5d | 0d | 50% |  | 2017-07-17 08:00 |  | 2017-07-21 17:00
1.1.1 | #1 Sprint - Análise Inicial | 5d | 0d | 50% |  | 2017-07-17 08:00 |  | 2017-07-21 17:00
1.1.1.1 | Plano de Comunicação | 3d | 0d | 50% | 2017-08-01 08:00 | 2017-07-17 08:00 |  | 2017-07-19 17:00
1.1.1.2 | Justificativa | 3d | 0d | 50% | 2017-07-31 08:00 | 2017-07-17 08:00 |  | 2017-07-19 17:00
1.1.1.3 | Objetivos | 3d | 0d | 50% | 2017-07-24 08:00 | 2017-07-19 08:00 |  | 2017-07-21 17:00
1.1.1.4 | Missão | 3d | 0d | 50% | 2017-08-01 08:00 | 2017-07-19 08:00 |  | 2017-07-21 17:00
1.2 | Planejamento | 23d | 0d | 20% |  | 2017-07-31 08:00 |  | 2017-08-30 17:00
1.2.1 | #2 Sprint - Análise I | 21d | 0d | 39% |  | 2017-07-31 08:00 |  | 2017-08-28 17:00
1.2.1.1 | Diagrama de Casos de Uso | 7d | 0d | 0% |  | 2017-07-31 08:00 |  | 2017-08-08 17:00
1.2.1.2 | Gráfico de Gantt | 5d | 0d | 51% | 2017-08-03 08:00 | 2017-07-31 08:00 |  | 2017-08-04 17:00
1.2.1.3 | Levantamento de Requisitos | 20d | 0d | 20% | 2017-07-17 08:00 | 2017-08-01 08:00 |  | 2017-08-28 17:00
1.2.1.4 | Análise da Concorrência | 2d | 0d | 95% | 2017-08-01 08:00 | 2017-08-01 08:00 | 2017-08-02 17:00 | 2017-08-02 17:00
1.2.1.5 | WBS | 8d | 0d | 100% | 2017-08-02 08:00 | 2017-07-31 08:00 | 2017-08-09 17:00 | 2017-08-09 17:00
1.2.2 | #3 Sprint - Análise II | 17d | 0d | 0% |  | 2017-07-31 08:00 |  | 2017-08-22 17:00
1.2.2.1 | Protótipo das Telas | 5d | 0d | 0% |  | 2017-08-04 08:00 |  | 2017-08-10 17:00
1.2.2.2 | Especificação dos Casos de Uso | 8d | 0d | 0% |  | 2017-08-10 08:00 |  | 2017-08-21 17:00
1.2.2.3 | Diagrama de Classes | 5d | 0d | 0% |  | 2017-08-16 08:00 |  | 2017-08-22 17:00
1.2.2.4 | Plano de Riscos | 5d | 0d | 0% |  | 2017-07-31 08:00 |  | 2017-08-04 17:00
1.2.3 | #4 Sprint - Análise III | 8d | 0d | 0% |  | 2017-08-21 08:00 |  | 2017-08-30 17:00
1.2.3.1 | Diagrama de Fluxo de Dados | 8d | 0d | 0% |  | 2017-08-21 08:00 |  | 2017-08-30 17:00
1.2.3.2 | Diagrama de Sequência | 8d | 0d | 0% |  | 2017-08-21 08:00 |  | 2017-08-30 17:00
1.3 | Execução | 35d | 0d | 0% |  | 2017-08-28 08:00 |  | 2017-10-13 17:00
1.3.1 | #5 Sprint - Desenvolvimento I | 12d | 0d | 0% |  | 2017-08-28 08:00 |  | 2017-09-12 17:00
1.3.1.1 | Interface | 7d | 0d | 0% |  | 2017-08-28 08:00 |  | 2017-09-05 17:00
1.3.1.2 | Login | 3d | 0d | 0% |  | 2017-08-28 08:00 |  | 2017-08-30 17:00
1.3.1.3 | CRUD de Usuário | 10d | 0d | 0% |  | 2017-08-30 08:00 |  | 2017-09-12 17:00
1.3.2 | #6 Sprint - Desenvolvimento II | 20d | 0d | 0% |  | 2017-09-18 08:00 |  | 2017-10-13 17:00
1.3.2.1 | CRUD de Receitas | 20d | 0d | 0% |  | 2017-09-18 08:00 |  | 2017-10-13 17:00
1.3.2.2 | Scanner | 7d | 0d | 0% |  | 2017-09-18 08:00 |  | 2017-09-26 17:00
1.3.2.3 | Cálculo da Informações | 15d | 0d | 0% |  | 2017-09-25 08:00 |  | 2017-10-13 17:00
1.4 | Controle | 12d | 0d | 0% |  | 2017-10-16 08:00 |  | 2017-10-31 17:00
1.4.1 | #7 Sprint - Testes | 12d | 0d | 0% |  | 2017-10-16 08:00 |  | 2017-10-31 17:00
1.4.1.1 | Planejamento de Testes | 4d | 0d | 0% |  | 2017-10-16 08:00 |  | 2017-10-19 17:00
1.4.1.2 | Testes Unitários | 8d | 0d | 0% |  | 2017-10-20 08:00 |  | 2017-10-31 17:00
1.4.1.3 | Testes de Integração | 8d | 0d | 0% |  | 2017-10-20 08:00 |  | 2017-10-31 17:00
1.4.1.4 | Testes Funcionais | 8d | 0d | 0% |  | 2017-10-20 08:00 |  | 2017-10-31 17:00
1.5 | Encerramento | 19d | 0d | 0% |  | 2017-11-06 08:00 |  | 2017-11-30 17:00
1.5.1 | #8 Sprint - Finalização | 19d | 0d | 0% |  | 2017-11-06 08:00 |  | 2017-11-30 17:00
1.5.1.1 | Entrega Documentação | 8d | 0d | 0% |  | 2017-11-06 08:00 |  | 2017-11-15 17:00
1.5.1.2 | Apresentação | 1d | 0d | 0% |  | 2017-11-30 08:00 |  | 2017-11-30 17:00
1.5.1.3 | Públicação na Google Play | 1d | 0d | 0% |  | 2017-11-06 08:00 |  | 2017-11-06 17:00

## TempData (hidden)
Work- | Baseline Work- | Actual Work- | Work Variance- | Remaining Work- | Cost- | Baseline Cost- | Actual Cost- | Fixed Cost- | Cost Variance- | Remaining Cost- | BCWP- | BCWS- | SV- | Name+ | Notes+ | WBS+ | Constraint Type+ | Constraint Date= | Critical+ | Delay- | Free Slack- | Total Slack- | ID- | Milestone+ | Priority+ | Subproject+ | Baseline Duration- | Actual Duration- | Duration- | Duration Variance- | Remaining Duration- | Percent Complete-[% Complete] | Percent Work Complete-[% Work Complete] | Start= | Finish= | Early Start= | Early Finish= | Late Start= | Late Finish= | Actual Start= | Actual Finish= | Baseline Start= | Baseline Finish= | Start Variance- | Finish Variance- | Predecessors+ | Successors+ | Resource Names+ | Resource Initials+ | Text1+ | Start1= | Finish1= | Text2+ | Start2= | Finish2= | Text3+ | Start3= | Finish3= | Text4+ | Start4= | Finish4= | Text5+ | Start5= | Finish5= | Text6+ | Text7+ | Text8+ | Text9+ | Text10+ | Marked+ | Flag1+ | Flag2+ | Flag3+ | Flag4+ | Flag5+ | Flag6+ | Flag7+ | Flag8+ | Flag9+ | Flag10+ | Rollup+ | CV- | Project+ | Outline Level- | Unique ID- | Number1- | Number2- | Number3- | Number4- | Number5- | Summary+ | Created= | Unique ID Predecessors+ | Unique ID Successors+ | Objects- | Linked Fields+ | Resume= | Stop= | Resume No Earlier Than= | Outline Number+ | Duration1- | Duration2- | Duration3- | Cost1- | Cost2- | Cost3- | Hide Bar+ | Confirmed+ | Update Needed+ | Contact+ | Resource Group+ | ACWP- | Type+ | Recurring+ | Effort Driven+ | Overtime Work- | Actual Overtime Work- | Remaining Overtime Work- | Regular Work- | Overtime Cost- | Actual Overtime Cost- | Remaining Overtime Cost- | Fixed Cost Accrual+ | Hyperlink+ | Hyperlink Address+ | Hyperlink SubAddress+ | Hyperlink Href+ | Assignment+ | Overallocated+ | External Task+ | Subproject Read Only+ | Response Pending+ | TeamStatus Pending+ | Leveling Can Split+ | Level Assignments+ | Work Contour+ | Cost4- | Cost5- | Cost6- | Cost7- | Cost8- | Cost9- | Cost10- | Date1= | Date2= | Date3= | Date4= | Date5= | Date6= | Date7= | Date8= | Date9= | Date10= | Duration4- | Duration5- | Duration6- | Duration7- | Duration8- | Duration9- | Duration10- | Start6= | Finish6= | Start7= | Finish7= | Start8= | Finish8= | Start9= | Finish9= | Start10= | Finish10= | Flag11+ | Flag12+ | Flag13+ | Flag14+ | Flag15+ | Flag16+ | Flag17+ | Flag18+ | Flag19+ | Flag20+ | Number6- | Number7- | Number8- | Number9- | Number10- | Number11- | Number12- | Number13- | Number14- | Number15- | Number16- | Number17- | Number18- | Number19- | Number20- | Text11+ | Text12+ | Text13+ | Text14+ | Text15+ | Text16+ | Text17+ | Text18+ | Text19+ | Text20+ | Text21+ | Text22+ | Text23+ | Text24+ | Text25+ | Text26+ | Text27+ | Text28+ | Text29+ | Text30+ | Assignment Delay- | Assignment Units- | Cost Rate Table+ | Preleveled Start= | Preleveled Finish= | WBS Predecessors+ | WBS Successors+ | Deadline= | Outline Code1+ | Outline Code2+ | Outline Code3+ | Outline Code4+ | Outline Code5+ | Outline Code6+ | Outline Code7+ | Outline Code8+ | Outline Code9+ | Outline Code10+ | Status+ | Physical Percent Complete-[Physical % Complete] | SVPercent- | CVPercent- | Calendar+
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Nutrinfo |  | 1 | O mais breve possível |  | Sim | 0d | 0d | 0d | 1 | Não | Mínima |  | 0d | 11,88d | 99d | 99d | 87,12d | 12% | 0% | 2017-07-17 08:00 | 2017-11-30 17:00 | 2017-07-17 08:00 | 2017-11-30 17:00 | 2017-07-31 08:00 | 2017-11-30 17:00 | 2017-07-17 08:00 |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 1 | 1 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Iniciação |  | 1.1 | O mais breve possível |  | Não | 0d | 94d | 94d | 2 | Não | Mínima |  | 0d | 2,5d | 5d | 5d | 2,5d | 50% | 0% | 2017-07-17 08:00 | 2017-07-21 17:00 | 2017-07-17 08:00 | 2017-07-21 17:00 | 2017-11-28 08:00 | 2017-11-30 17:00 | 2017-07-17 08:00 |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 2 | 40 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | #1 Sprint - Análise Inicial |  | 1.1.1 | O mais breve possível |  | Não | 0d | 94d | 94d | 3 | Não | Mínima |  | 0d | 2,5d | 5d | 5d | 2,5d | 50% | 0% | 2017-07-17 08:00 | 2017-07-21 17:00 | 2017-07-17 08:00 | 2017-07-21 17:00 | 2017-11-28 08:00 | 2017-11-30 17:00 | 2017-07-17 08:00 |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 3 | 97 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.1.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Plano de Comunicação |  | 1.1.1.1 | O mais breve possível |  | Não | 0d | 96d | 96d | 4 | Não | Mínima |  | 0d | 1,5d | 3d | 3d | 1,5d | 50% | 0% | 2017-07-17 08:00 | 2017-07-19 17:00 | 2017-07-17 08:00 | 2017-07-19 17:00 | 2017-11-28 08:00 | 2017-11-30 17:00 | 2017-07-17 08:00 |  | 2017-08-01 08:00 |  | -11d | -12d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 98 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.1.1.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Justificativa |  | 1.1.1.2 | Não iniciar antes de | 2017-07-17 08:00 | Não | 0d | 96d | 96d | 5 | Não | Mínima |  | 0d | 1,5d | 3d | 3d | 1,5d | 50% | 0% | 2017-07-17 08:00 | 2017-07-19 17:00 | 2017-07-17 08:00 | 2017-07-19 17:00 | 2017-11-28 08:00 | 2017-11-30 17:00 | 2017-07-17 08:00 |  | 2017-07-31 08:00 |  | -10d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 99 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.1.1.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Objetivos |  | 1.1.1.3 | Não iniciar antes de | 2017-07-19 08:00 | Não | 0d | 94d | 94d | 6 | Não | Mínima |  | 0d | 1,5d | 3d | 3d | 1,5d | 50% | 0% | 2017-07-19 08:00 | 2017-07-21 17:00 | 2017-07-19 08:00 | 2017-07-21 17:00 | 2017-11-28 08:00 | 2017-11-30 17:00 | 2017-07-19 08:00 |  | 2017-07-24 08:00 |  | -3d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 100 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.1.1.3 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Missão |  | 1.1.1.4 | Não iniciar antes de | 2017-07-19 08:00 | Não | 0d | 94d | 94d | 7 | Não | Mínima |  | 0d | 1,5d | 3d | 3d | 1,5d | 50% | 0% | 2017-07-19 08:00 | 2017-07-21 17:00 | 2017-07-19 08:00 | 2017-07-21 17:00 | 2017-11-28 08:00 | 2017-11-30 17:00 | 2017-07-19 08:00 |  | 2017-08-01 08:00 |  | -9d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 101 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.1.1.4 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Planejamento |  | 1.2 | O mais breve possível |  | Sim | 0d | 0d | 0d | 8 | Não | Mínima |  | 0d | 4,6d | 23d | 23d | 18,4d | 20% | 0% | 2017-07-31 08:00 | 2017-08-30 17:00 | 2017-07-31 08:00 | 2017-08-30 17:00 | 2017-07-31 08:00 | 2017-11-30 17:00 | 2017-07-31 08:00 |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 2 | 28 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | #2 Sprint - Análise I |  | 1.2.1 | O mais breve possível |  | Sim | 0d | 0d | 0d | 9 | Não | Mínima |  | 0d | 8,19d | 21d | 21d | 12,81d | 39% | 0% | 2017-07-31 08:00 | 2017-08-28 17:00 | 2017-07-31 08:00 | 2017-08-28 17:00 | 2017-07-31 08:00 | 2017-11-30 17:00 | 2017-07-31 08:00 |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 3 | 77 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.2.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Diagrama de Casos de Uso |  | 1.2.1.1 | Não iniciar antes de | 2017-07-31 08:00 | Não | 0d | 82d | 82d | 10 | Não | Mínima |  | 0d | 0d | 7d | 7d | 7d | 0% | 0% | 2017-07-31 08:00 | 2017-08-08 17:00 | 2017-07-31 08:00 | 2017-08-08 17:00 | 2017-11-22 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 78 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.1.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Gráfico de Gantt |  | 1.2.1.2 | Não iniciar antes de | 2017-07-31 08:00 | Não | 0d | 84d | 84d | 11 | Não | Mínima |  | 0d | 2,55d | 5d | 5d | 2,45d | 51% | 0% | 2017-07-31 08:00 | 2017-08-04 17:00 | 2017-07-31 08:00 | 2017-08-04 17:00 | 2017-11-24 08:00 | 2017-11-30 17:00 | 2017-07-31 08:00 |  | 2017-08-03 08:00 |  | -3d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 79 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.1.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Levantamento de Requisitos |  | 1.2.1.3 | Não iniciar antes de | 2017-08-01 08:00 | Não | 0d | 68d | 68d | 12 | Não | Mínima |  | 0d | 4d | 20d | 20d | 16d | 20% | 0% | 2017-08-01 08:00 | 2017-08-28 17:00 | 2017-08-01 08:00 | 2017-08-28 17:00 | 2017-11-03 08:00 | 2017-11-30 17:00 | 2017-08-01 08:00 |  | 2017-07-17 08:00 |  | 11d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 80 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.1.3 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Análise da Concorrência |  | 1.2.1.4 | Não iniciar antes de | 2017-08-01 08:00 | Não | 0d | 86d | 86d | 13 | Não | Mínima |  | 0d | 1,9d | 2d | 2d | 0,1d | 95% | 0% | 2017-08-01 08:00 | 2017-08-02 17:00 | 2017-08-01 08:00 | 2017-08-02 17:00 | 2017-11-29 08:00 | 2017-11-30 17:00 | 2017-08-01 08:00 |  | 2017-08-01 08:00 | 2017-08-02 17:00 | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 81 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.1.4 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | WBS |  | 1.2.1.5 | O mais breve possível |  | Não | 0d | 0d | 0d | 14 | Não | Mínima |  | 0d | 8d | 8d | 8d | 0d | 100% | 0% | 2017-07-31 08:00 | 2017-08-09 17:00 | 2017-07-31 08:00 | 2017-08-09 17:00 | 2017-07-31 08:00 | 2017-08-09 17:00 | 2017-07-31 08:00 | 2017-08-09 17:00 | 2017-08-02 08:00 | 2017-08-09 17:00 | -2d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 82 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.1.5 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | #3 Sprint - Análise II |  | 1.2.2 | O mais breve possível |  | Não | 0d | 72d | 72d | 15 | Não | Mínima |  | 0d | 0d | 17d | 17d | 17d | 0% | 0% | 2017-07-31 08:00 | 2017-08-22 17:00 | 2017-07-31 08:00 | 2017-08-22 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 3 | 83 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.2.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Protótipo das Telas |  | 1.2.2.1 | Não iniciar antes de | 2017-08-04 08:00 | Não | 0d | 80d | 80d | 16 | Não | Mínima |  | 0d | 0d | 5d | 5d | 5d | 0% | 0% | 2017-08-04 08:00 | 2017-08-10 17:00 | 2017-08-04 08:00 | 2017-08-10 17:00 | 2017-11-24 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 84 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.2.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Especificação dos Casos de Uso |  | 1.2.2.2 | Não iniciar antes de | 2017-08-10 08:00 | Não | 0d | 73d | 73d | 17 | Não | Mínima |  | 0d | 0d | 8d | 8d | 8d | 0% | 0% | 2017-08-10 08:00 | 2017-08-21 17:00 | 2017-08-10 08:00 | 2017-08-21 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 85 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.2.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Diagrama de Classes |  | 1.2.2.3 | Não iniciar antes de | 2017-08-16 08:00 | Não | 0d | 72d | 72d | 18 | Não | Mínima |  | 0d | 0d | 5d | 5d | 5d | 0% | 0% | 2017-08-16 08:00 | 2017-08-22 17:00 | 2017-08-16 08:00 | 2017-08-22 17:00 | 2017-11-24 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 86 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.2.3 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Plano de Riscos |  | 1.2.2.4 | Não iniciar antes de | 2017-07-31 08:00 | Não | 0d | 84d | 84d | 19 | Não | Mínima |  | 0d | 0d | 5d | 5d | 5d | 0% | 0% | 2017-07-31 08:00 | 2017-08-04 17:00 | 2017-07-31 08:00 | 2017-08-04 17:00 | 2017-11-24 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 87 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.2.4 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | #4 Sprint - Análise III |  | 1.2.3 | O mais breve possível |  | Não | 0d | 66d | 66d | 20 | Não | Mínima |  | 0d | 0d | 8d | 8d | 8d | 0% | 0% | 2017-08-21 08:00 | 2017-08-30 17:00 | 2017-08-21 08:00 | 2017-08-30 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 3 | 65 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.2.3 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Diagrama de Fluxo de Dados |  | 1.2.3.1 | Não iniciar antes de | 2017-08-21 08:00 | Não | 0d | 66d | 66d | 21 | Não | Mínima |  | 0d | 0d | 8d | 8d | 8d | 0% | 0% | 2017-08-21 08:00 | 2017-08-30 17:00 | 2017-08-21 08:00 | 2017-08-30 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 67 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.3.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Diagrama de Sequência |  | 1.2.3.2 | Não iniciar antes de | 2017-08-21 08:00 | Não | 0d | 66d | 66d | 22 | Não | Mínima |  | 0d | 0d | 8d | 8d | 8d | 0% | 0% | 2017-08-21 08:00 | 2017-08-30 17:00 | 2017-08-21 08:00 | 2017-08-30 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 66 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.2.3.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Execução |  | 1.3 | O mais breve possível |  | Não | 0d | 34d | 34d | 23 | Não | Mínima |  | 0d | 0d | 35d | 35d | 35d | 0% | 0% | 2017-08-28 08:00 | 2017-10-13 17:00 | 2017-08-28 08:00 | 2017-10-13 17:00 | 2017-11-03 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 2 | 26 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.3 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | #5 Sprint - Desenvolvimento I |  | 1.3.1 | O mais breve possível |  | Não | 0d | 57d | 57d | 24 | Não | Mínima |  | 0d | 0d | 12d | 12d | 12d | 0% | 0% | 2017-08-28 08:00 | 2017-09-12 17:00 | 2017-08-28 08:00 | 2017-09-12 17:00 | 2017-11-17 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 3 | 88 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.3.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Interface |  | 1.3.1.1 | Não iniciar antes de | 2017-08-28 08:00 | Não | 0d | 62d | 62d | 25 | Não | Mínima |  | 0d | 0d | 7d | 7d | 7d | 0% | 0% | 2017-08-28 08:00 | 2017-09-05 17:00 | 2017-08-28 08:00 | 2017-09-05 17:00 | 2017-11-22 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 89 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.3.1.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Login |  | 1.3.1.2 | Não iniciar antes de | 2017-08-28 08:00 | Não | 0d | 66d | 66d | 26 | Não | Mínima |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2017-08-28 08:00 | 2017-08-30 17:00 | 2017-08-28 08:00 | 2017-08-30 17:00 | 2017-11-28 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 90 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.3.1.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | CRUD de Usuário |  | 1.3.1.3 | Não iniciar antes de | 2017-08-30 08:00 | Não | 0d | 57d | 57d | 27 | Não | Mínima |  | 0d | 0d | 10d | 10d | 10d | 0% | 0% | 2017-08-30 08:00 | 2017-09-12 17:00 | 2017-08-30 08:00 | 2017-09-12 17:00 | 2017-11-17 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 91 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.3.1.3 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | #6 Sprint - Desenvolvimento II |  | 1.3.2 | O mais breve possível |  | Não | 0d | 34d | 34d | 28 | Não | Mínima |  | 0d | 0d | 20d | 20d | 20d | 0% | 0% | 2017-09-18 08:00 | 2017-10-13 17:00 | 2017-09-18 08:00 | 2017-10-13 17:00 | 2017-11-03 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 3 | 72 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.3.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | CRUD de Receitas |  | 1.3.2.1 | Não iniciar antes de | 2017-09-18 08:00 | Não | 0d | 34d | 34d | 29 | Não | Mínima |  | 0d | 0d | 20d | 20d | 20d | 0% | 0% | 2017-09-18 08:00 | 2017-10-13 17:00 | 2017-09-18 08:00 | 2017-10-13 17:00 | 2017-11-03 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 76 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.3.2.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Scanner |  | 1.3.2.2 | Não iniciar antes de | 2017-09-18 08:00 | Não | 0d | 47d | 47d | 30 | Não | Mínima |  | 0d | 0d | 7d | 7d | 7d | 0% | 0% | 2017-09-18 08:00 | 2017-09-26 17:00 | 2017-09-18 08:00 | 2017-09-26 17:00 | 2017-11-22 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 74 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.3.2.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Cálculo da Informações |  | 1.3.2.3 | Não iniciar antes de | 2017-09-25 08:00 | Não | 0d | 34d | 34d | 31 | Não | Mínima |  | 0d | 0d | 15d | 15d | 15d | 0% | 0% | 2017-09-25 08:00 | 2017-10-13 17:00 | 2017-09-25 08:00 | 2017-10-13 17:00 | 2017-11-10 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 73 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.3.2.3 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Controle |  | 1.4 | O mais breve possível |  | Não | 0d | 22d | 22d | 32 | Não | Mínima |  | 0d | 0d | 12d | 12d | 12d | 0% | 0% | 2017-10-16 08:00 | 2017-10-31 17:00 | 2017-10-16 08:00 | 2017-10-31 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 2 | 19 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.4 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | #7 Sprint - Testes |  | 1.4.1 | O mais breve possível |  | Não | 0d | 22d | 22d | 33 | Não | Mínima |  | 0d | 0d | 12d | 12d | 12d | 0% | 0% | 2017-10-16 08:00 | 2017-10-31 17:00 | 2017-10-16 08:00 | 2017-10-31 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 3 | 36 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.4.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Planejamento de Testes |  | 1.4.1.1 | Não iniciar antes de | 2017-10-16 08:00 | Não | 0d | 30d | 30d | 34 | Não | Mínima |  | 0d | 0d | 4d | 4d | 0d | 0% | 0% | 2017-10-16 08:00 | 2017-10-19 17:00 | 2017-10-16 08:00 | 2017-10-19 17:00 | 2017-11-27 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 107 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.4.1.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Testes Unitários |  | 1.4.1.2 | Não terminar antes de | 2017-10-31 17:00 | Não | 0d | 22d | 22d | 35 | Não | Mínima |  | 0d | 0d | 8d | 8d | 15d | 0% | 0% | 2017-10-20 08:00 | 2017-10-31 17:00 | 2017-10-20 08:00 | 2017-10-31 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 102 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.4.1.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Testes de Integração |  | 1.4.1.3 | Não terminar antes de | 2017-10-31 17:00 | Não | 0d | 22d | 22d | 36 | Não | Mínima |  | 0d | 0d | 8d | 8d | 0d | 0% | 0% | 2017-10-20 08:00 | 2017-10-31 17:00 | 2017-10-20 08:00 | 2017-10-31 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 106 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.4.1.3 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Testes Funcionais |  | 1.4.1.4 | Não terminar antes de | 2017-10-31 17:00 | Não | 0d | 22d | 22d | 37 | Não | Mínima |  | 0d | 0d | 8d | 8d | 0d | 0% | 0% | 2017-10-20 08:00 | 2017-10-31 17:00 | 2017-10-20 08:00 | 2017-10-31 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 105 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.4.1.4 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Encerramento |  | 1.5 | O mais breve possível |  | Sim | 0d | 0d | 0d | 38 | Não | Mínima |  | 0d | 0d | 19d | 19d | 19d | 0% | 0% | 2017-11-06 08:00 | 2017-11-30 17:00 | 2017-11-06 08:00 | 2017-11-30 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 2 | 2 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.5 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | #8 Sprint - Finalização |  | 1.5.1 | O mais breve possível |  | Sim | 0d | 0d | 0d | 39 | Não | Mínima |  | 0d | 0d | 19d | 19d | 19d | 0% | 0% | 2017-11-06 08:00 | 2017-11-30 17:00 | 2017-11-06 08:00 | 2017-11-30 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 3 | 4 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Sim |  |  |  | 0 | Não |  |  |  | 1.5.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Entrega Documentação |  | 1.5.1.1 | Não iniciar antes de | 2017-11-06 08:00 | Não | 0d | 11d | 11d | 40 | Não | Mínima |  | 0d | 0d | 8d | 8d | 8d | 0% | 0% | 2017-11-06 08:00 | 2017-11-15 17:00 | 2017-11-06 08:00 | 2017-11-15 17:00 | 2017-11-21 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 108 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.5.1.1 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Apresentação |  | 1.5.1.2 | Não iniciar antes de | 2017-11-30 08:00 | Sim | 0d | 0d | 0d | 41 | Não | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2017-11-30 08:00 | 2017-11-30 17:00 | 2017-11-30 08:00 | 2017-11-30 17:00 | 2017-11-30 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 93 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.5.1.2 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)
0h | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | Públicação na Google Play |  | 1.5.1.3 | Não iniciar antes de | 2017-11-06 08:00 | Não | 0d | 18d | 18d | 42 | Não | Mínima |  | 0d | 0d | 1d | 1d | 0d | 0% | 0% | 2017-11-06 08:00 | 2017-11-06 17:00 | 2017-11-06 08:00 | 2017-11-06 17:00 | 2017-11-30 08:00 | 2017-11-30 17:00 |  |  |  |  | 0d | 0d | [24 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | R$ 0,00 |  | 4 | 92 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | Não |  |  |  | 0 | Não |  |  |  | 1.5.1.3 | 0d | 0d | 0d | R$ 0,00 | R$ 0,00 | R$ 0,00 | Não | Não | Não |  |  | R$ 0,00 | Unidades fixas | Não | Sim | 0h | 0h | 0h | 0h | R$ 0,00 | R$ 0,00 | R$ 0,00 | Rateado |  |  |  |  | Não | Não | Não | Não | Não | Não | Não | Não | Flat | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | R$ 0,00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | Não | Não | Não | Não | Não | Não | Não | Não | Não | Não | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | [20 empty] | 0d | 0% | A | [16 empty] | 0% | 0% | 0% | Project Default (Standard)